| Month | Activities | Detailed Tasks | Expected Deliverables |
| --- | --- | --- | --- |
| 1 | Literature Review & Dataset Selection | Study recent research papers on image recognition robustness, occlusion, and noise Identify research gaps related to pattern recognition failure Select suitable datasets (MNIST, simple object images) Define evaluation strategy and degradation parameters | Literature review summary Selected dataset(s) Finalized problem formulation |
| 2 | Data Preprocessing & Degradation Implementation | Image normalization and resizing Dataset cleaning and formatting Implementation of progressive degradation techniques (pixel removal, masking, noise, blur) Verification of degraded datasets | Preprocessed dataset Degraded dataset versions Data preparation scripts |
| 3 | Model Development & Training | Design and implementation of baseline CNN model Training model on clean dataset Training model on progressively degraded datasets Hyperparameter tuning (learning rate, epochs) | Trained recognition models Training logs and accuracy reports |
| 4 | Testing, Evaluation & Result Analysis | Model testing on unseen degraded data Performance evaluation using accuracy, precision, recall, and F1-score Generation of accuracy vs information loss graphs Identification of recognition breakpoints | Evaluation results Graphs and performance tables Breakpoint analysis |
| 5 | Documentation & Final Report Preparation | Interpretation of experimental results Discussion of limitations and future work Writing final project report and proposal refinement Preparation of presentation slides (if required) | Final project report Figures and tables Presentation materials |